## Scope
Scope and high level solution/approach
Description of JIRA : EAISA-54 ROM -Previous LBA amount to be added to the calculation when it's the first time a LBA has ever been done in AIS Requirements: The "LBA" tab in AIS is where users can enter a dollar amount to be added to the calculation when it's the first time a LBA has ever been done in AIS. This field is recognized only when it's the first adjustment done in AIS .So we need to introduce a new checkbox field in LBA Tab and rewrite the logic of the stored procedure in such a way that if the new checkbox is checked then should consider the amount which was entered by the user at any no of adjustment. Activities Considered for Estimates (Hours) Analysis - 28 Design - 0 Development - 60 Testing - 45 Implementation - 12

## Detailed Estimate & Assumptions
EAISA-54-Previous LBA to be added to the calculation when it's the first time a LBA has ever been done in AIS | Analysis (Hours) | Design, Development (Hours) | Testing (Hours) | Post - Production Validation (Hours) | Comments, Assumptions and Dependencies
Technology 1 Estimate | 28 | 60 | 45 | 12 | Assumptions: As per our analysis we have found that previously LBA are getting calculated using an stored procedure where it is checking whether the adjustment is initial adjustment or not. As per the logic written in the stored procedure, if that is initial adjustment it will consider the amount which was entered by the user in the LBA field in LBA Setup tab in LBA Info page. If it is not initial adjustment, then it will not consider the amount which was entered by the user in LBA field, it will take 0 and it will calculate from previous adjustments belongs to the same Program period. So we need to introduce a new checkbox field in LBA Tab and rewrite the logic of the stored procedure in such a way that if the new checkbox is checked then should consider the amount which was entered by the user at any no of adjustment. if that is empty we should calculate from previous adjustment belongs to program period in ais history.
Total | 145

## Effort & Cost
EAISA-54-PreviousLBA amount to be added to the calculation when it's the first time a LBA has ever been done in AIS | Effort (Person Hours)
Technology 1 | 145
Admin | 0
DBA | 0
PM (10%) | 14.5
Total | 159.5
Role | Effort (Person Hours) | Rate | Cost
Technology 1 - Onshore | 43.5 | 33.05 | 1437.675
Technology 1 - Offshore | 101.5 | 33.05 | 3354.575
PM - Onshore | 14.5 | 106.64 | 1546.28
Total | 159.5 |  | 6338.53